## Slide 1: Sponsor Engagement Stakeholder Analysis Effective Interviewing
DAEN 459/460 Capstone Senior Design
Alexander Abuabara
Fall 2026

## Slide 2: The Goal is: Shared Confidence Not Just Frequent Contact
Set a sponsor cadence that produces decisions
Identify whose needs can reshape the solution
Run conversation/interviews that reveal workflow, constraints, and evidence
Convert conversations into testable requirements
A useful sponsor meeting ends with:
1) Decisions
2) Owners
3) Evidence needed
4) Next checkpoint

## Slide 3: Example Riverton Public Works (Sponsor)
Case Reduce missed pickups without creating surveillance
Use service-request, route, and weather data to help supervisors anticipate missed pickups.
First request: "Build us a dashboard that predicts tomorrow's problem routes."

## Slide 4: What is Still Unknown?
Who acts on a prediction?
What counts as a "miss"?
Which errors are unacceptable?
What data can legally be used?
How will success be judged?

## Slide 5: Use Sponsor Time to Reduce Uncertainty in Stages
ALIGN
Problem, Outcomes, Roles
Kickoff + weekly decision log
DISCOVER
Workflows, Data, Constraints
1–2 interviews/month
TEST
Assumptions, Prototype, Tradeoffs
Biweekly demo with users
TRANSFER
Adoption, Ownership, Handoff
Runbook + adoption check
Rule
Every interaction should close an uncertainty, confirm a decision, or expose a new risk.

## Slide 6: Agree on the "Working Contract" Before the Work Accelerates
DECISION RIGHTS | What can the team decide?
AVAILABILITY | Who joins which meeting? Who may be the backup?
FEEDBACK WINDOW | When is silence treated as approval?
ESCALATION PATH | What happens when scope, data, or access stalls?

## Slide 7: Map Influence x Impact (Then Plan Distinct Engagement)
For each stakeholder:
Desired outcome
Fears / constraints
Evidence they trust
Decision power
Best channel

## Slide 8: A Stakeholder Register Turns a Map into an Engagement Plan
Stakeholder | What They Need | Project Risk | Evidence to Seek | Engagement
Public Works Director | Fewer complaints; defensible spend | Dashboard optimizes the wrong outcome | Definition of success; decision thresholds | Bi-monthly decision review
Route Supervisors | Fewer complaints; defensible spend | Alerts arrive too late or lack context | Daily workflow; override reasons | Co-design + prototype tests
Drivers | Fair, feasible assignments | Model penalizes crews for bad inputs | Exception patterns; route realities | Short interviews; ride-along
Residents | Reliable service; privacy | Sensitive data used without consent | Complaint journey; acceptable data use | Survey + representative interviews
IT /Privacy | Secure, supportable solution | Unauthorized data or unsupported stack | Access rules; retention; architecture | Gate reviews

## Slide 9: Interview for Decisions and Behavior (Not Feature Votes)
Weak
"Would a predictive dashboard help you?"
  Invites politeness and speculation
Better
"Walk me through the last missed pickup you handled."
  Reveals actual workflow and evidence
Target: Concrete Episodes → Observed Constraints → Decision Criteria → Testable Requirements

## Slide 10: Strong Interviews Follow the Story Before Testing Solutions
CONTEXT
EPISODE
PROBE
REFLECT
CLOSE
Role, goals, environment
Last real event, step by step
Why? What changed? Show me.
Tradeoffs, workarounds, trust
Missing voices, artifacts, follow-up
Listen for verbs, exceptions, handoffs, artifacts, and consequences.

## Slide 11: Use a question ladder to move from story to requirement
OPEN Tell me about the last missed pickup.
SEQUENCE What happened first? Then what?
PROBE What information did you use? What was missing?
EXCEPTION When does this process break down?
CRITERION What would make an alert trustworthy enough to act on?
Avoid: Leading Questions • Stacked Questions • Jargon • Defending the Solution

## Slide 12: Example: One answer changes the product concept
Interview Excerpt
Supervisor: "By the time I see the complaint report, the truck is already across town. I usually call the driver because the route system does not show blocked alleys."
SIGNAL | Complaint report is delayed
WORKAROUND | Supervisor calls the driver
HIDDEN CONTEXT | Blocked alleys are absent from route data
REQUIREMENT | Surface operational exceptions before dispatch
TEST | Can a supervisor act in under 2 minutes?
The pivot:
From predicting problem routes
To supporting exception-aware dispatch

## Slide 13: Synthesize Immediately: Evidence, Interpretation, Decision
EVIDENCE
Exact observation or short quote
+ source and date
INTERPRETATION
Pattern, tension, or unmet need
+ confidence level
Do not jump
Quote → feature
Build the chain
Evidence → insight → decision → test
ACTION
Requirement, experiment, or question
+ owner and deadline

## Slide 14: Practice: Interview the Route Supervisor
Debrief:
What changed in your understanding?
What requirement can you now test?
INTERVIEWER
Use the five-step arc. Ask for one real episode.
SUPERVISOR
You distrust alerts without route context. Reveal this only if probed.
OBSERVER
Track leading questions, follow-ups, and usable evidence.

## Slide 15: Next Sponsor Meeting: Leave with Four Artifacts
Working Contract Decision rights, cadence, feedback, escalation
Stakeholder Register Influence, impact, needs, evidence, channel
Interview Guide Purpose, arc, probes, closing questions
Decision Log Evidence, decision, owner, due date!
Evidence → Insight → Decision → Test